## Sheet1
S.No/Week | Date | Task Name | Status (% of completion)
Week1 | 2022-12-05 | KT | 10%
| 2022-12-06 | KT | 20%
| 2022-12-07 | KT | 40%
| 2022-12-08 | KT | 60%
| 2022-12-09 | KT | 100%
| 2022-12-10 | Saturday | -
| 2022-12-11 | Sunday | -
Week2 | 2022-12-12 | System setup | 10%
| 2022-12-13 | System setup &Software installation | 100%
| 2022-12-14 | Software installation | 40%
| 2022-12-15 | Software installation | 60%
| 2022-12-16 | Software installation | 100%
| 2022-12-17 | Saturday | -
| 2022-12-18 | Sunday | -
Week3 | 2022-12-19 | ROS2 KT | 50%
| 2022-12-20 | ROS2 KT | 100%
| 2022-12-21 | Carla installation setup | 40%
| 2022-12-22 | Carla installation setup | 100%
| 2022-12-23 | Carla KT | 100%
| 2022-12-24 | Saturday | -
| 2022-12-25 | Sunday | -
Week4 | 2022-12-26 | unstructured environment simulator exploring | 30%
| 2022-12-27 | unstructured environment simulator exploring | 60%
| 2022-12-28 | unstructured environment simulator exploring | 100%
| 2022-12-29 | Holiday | -
| 2022-12-30 | unstructured environment exploring & Chrono simulator setup | 50%
| 2022-12-31 | Saturday | -
| 2023-01-01 | Sunday | -
Week5 | 2023-01-02 | unstructured environment exploring & working on Chrono simulator setup issue | 100%
| 2023-01-03 | unstructured environment simulator exploring | 100%
| 2023-01-04 | carla unstructured/off-road environment simulator exploring and setup of carla 0.9.6 | 30%
| 2023-01-05 | carla unstructured/off-road environment simulator exploring and setup of carla 0.9.6 | 60%
| 2023-01-06 | carla unstructured/off-road environment simulator exploring and setup of carla 0.9.6 | 100%
| 2023-01-07 | Saturday | -
| 2023-01-08 | Sunday | -
Week6 | 2023-01-09 | carla unstructured/off-road environment simulator carla 0.9.10:basic Scripts setup | 100%
| 2023-01-10 | carla unstructured/off-road environment simulator carla 0.9.6:basic Scripts setup | 50%
| 2023-01-11 | carla unstructured/off-road environment simulator carla 0.9.6:basic Scripts setup | 100%
| 2023-01-12 | carla 0.9.10 structured simulator :basic Scripts setup for lidar | 10%
| 2023-01-13 | MAVS simulator exploring | 30%
| 2023-01-14 | Saturday | -
| 2023-01-15 | Sunday | -
Week7 | 2023-01-16 | On Leave | On Leave
| 2023-01-17 | MAVS simulator setup | 30%
| 2023-01-18 | MAVS simulator setup & creating Scripts for basic environment | 60%
| 2023-01-19 | MAVS creating Scripts for basic environment & Review with scientist about MAVS | 100%
| 2023-01-20 | carla 0.9.10 structured simulator :basic Scripts setup for lidar | 50%
| 2023-01-21 | Saturday | -
| 2023-01-22 | Sunday | -
Week8 | 2023-01-23 | carla 0.9.10 structured simulator :basic Scripts setup for lidar | 100%
| 2023-01-24 | carla 0.9.6 unstructured simulator :basic Scripts setup for lidar | 30%
| 2023-01-25 | carla 0.9.10 structured simulator : Scripts setup for lidar with point cloud data height map image in birdview | 50%
| 2023-01-26 | Holiday | -
| 2023-01-27 | carla 0.9.10 structured simulator : Scripts setup for lidar with point cloud data height map image in birdview | 90%
| 2023-01-28 | Saturday | -
| 2023-01-29 | Sunday | -
| 2023-01-30 | carla 0.9.6 unstructured simulator : Scripts setup for lidar with point cloud data height map image in birdview
2023-01-31
2023-02-01